## project
[56 empty] | PCB released to fab | [7 empty] | PCB back for assembly
Project Planner
[8 empty] | Period Highlight: |  |  |  |  | 15 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT |  | August 28th |  |  |  | September 1st | [29 empty] | October 1st | [30 empty] | November 1st | [29 empty] | December 1st | [15 empty] | Project Demos
ACTIVITY |  | START | DURATION | START | DURATION | COMPLETE |  | PERIODS
| Lead | [5 empty] | Comments | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116
Search Project Idea | Sanjana & Shekhar | 1 | 7 | 6 | 3 | 100%
Project proposal | Sanjana & Shekhar | 7 | 2 | 8 | 2 | 100%
Search for Part Kits | Sanjana & Shekhar | 11 | 3 | 11 | 3 | 100%
Research about Mesh Networks & other Radio Communication | Sanjana & Shekhar | 13 | 3 | 13 | 3 | 100%
Energy profile, determining current in each mode of operation | Sanjana & Shekhar | 16 | 1 | 17 | 1 | 100%
Decision on regulated and unregulated power supply | Sanjana & Shekhar | 17 | 1 | 18 | 1 | 100%
Battery Selection | Sanjana & Shekhar | 18 | 1 | 19 | 1 | 100%
Power Management Unit Selection | Sanjana & Shekhar | 20 | 1 | 20 | 1 | 100%
Project Update Report | Sanjana & Shekhar | 21 | 2 | 21 | 2 | 100%
Recalculating the peak current and energy supplied from the battery | Sanjana & Shekhar | 25 | 1 | 25 | 1 | 100%
Verified Energy storage element and PMU | Sanjana and Shekhar | 27 | 1 | 27 | 1 | 100%
Research and Analysis of Machine Learning Algorithms | Shekhar | 28 | 1 | 28 | 1 | 100%
Referring documentation on Bluetooth Mesh Network | Sanjana | 28 | 1 | 28 | 1 | 100%
Project Update Report | Sanjana and Shekhar | 29 | 2 | 29 | 2 | 100%
Reading about BLE Mesh | Shekhar | 31 | 2 | 31 | 2 | 100%
Designing a Power Circuit - First Pass Design | Shekhar | 33 | 2 | 33 | 2 | 100%
Energy Spike Calculation | Sanjana | 35 | 1 | 35 | 1 | 100%
Schematics - Partial | Sanjana | 36 | 1 | 36 | 1 | 100%
Simulation of Voltage Droop | Shekhar | 36 | 1 | 36 | 1 | 100%
Project Update Report | Sanjana and Shekhar | 37 | 2 | 37 | 2 | 100%
Determine how to program the MCU | Shekhar | 39 | 1 | 39 | 1 | 100%
Continue working on Schematics | Sanjana | 40 | 2 | 40 | 2 | 100%
Determine test points for signals | Shekhar | 41 | 1 | 41 | 1 | 100%
Working on Machine learning algorithms to identify a optimal algorithm for data extraction and prediction. | Shekhar | 42 | 2 | 42 | 2 | 100%
Finalise test points for signals | Shekhar | 42 | 1 | 42 | 1 | 100%
Work on BLE Mesh | Sanjana | 42 | 2 | 42 | 2 | 100%
Project Update Report | Sanjana and Shekhar | 45 | 1 | 45 | 1 | 100%
Schematics | Shekhar | 46 | 1 | 46 | 1 | 90%
Footprint of Ics | Sanjana | 47 | 2 | 47 | 2 | 60%
Board Layout | Sanjana and Shekhar | 48 | 2 | 48 | 2 | 50%
Worked on ESD diode selections | Sanjana and Shekhar | 48 | 1 | 51 | 1 | 100%
Project Update Report | Sanjana and Shekahr | 51 | 1 | 51 | 1 | 100%
Complete Schematic and Get Reviewed | Sanjana and Shekhar | 52 | 4 | 56 | 4 | 100%
Continue working on Layouts | Sanjana and Shekhar | 52 | 4 | 56 | 4 | 100%
Project Update Report | Sanjana and Shekhar | 56 | 1 | 56 | 1 | 100%
Circuit to isolate charging and discharging | Sanjana and Shekhar | 57 | 1 | 57 | 1 | 100%
Firmware development for Accelerometer | Sanjana | 58 | 1 | 58 | 1 | 10%
Continue working on BLE | Shekhar | 58 | 1 | 58 | 1 | 10%
Worked on Layout | Sanjana and Shekhar | 59 | 4 | 62 | 4 | 80%
Project Update Report | Sanjana and Shekhar | 63 | 1 | 63 | 1 | 100%
Worked on Layout and got reviewed | Sanjana and Shekhar | 64 | 3 | 64 | 3 | 100%
Working on BLE mesh | Shekhar | 67 | 1 | 67 | 1 | 15%
Continuing working on firmware | Sanjana | 67 | 1 | 67 | 1 | 15%
Project Update 9 | Sanjana and Shekhar | 69 | 1 | 69 | 1 | 100%
Finalised Parts based on all simulations and calculations | Sanjana and Shekhar | 60 | 2 | 71 | 2 | 100%
BOM | Sanjana and Shekhar | 62 | 2 | 73 | 2 | 100%
Work on BLE Mesh | Sanjana | 64 | 1 | 75 | 1 | 20%
Work on Machine learning for character identification | Shekhar | 64 | 1 | 76 | 1 | 20%
Project Update Report | Sanjana and Shekhar | 65 | 1 | 77 | 1 | 100%
Ordering of Parts | Sanjana | 68 | 1 | 78 | 1 | 100%
Ordering of MCU | Shekhar | 68 | 1 | 79 | 1 | 100%
Work on BLE Communication | Shekhar | 69 | 1 | 80 | 1 | 20%
Work on BLE Mesh | Sanjana | 69 | 2 | 80 | 2 | 20%
Work on Training for character identification | Shekhar | 70 | 2 | 90 | 2 | 100%
Project Update Report | Sanjana and Shekhar | 72 | 1 | 92 | 1 | 100%
Board Bringup | Sanjana and Shekhar | 74 | 2 | 94 | 2 | 100%
Testing of the Board | Sanjana and Shekhar | 77 | 3 | 97 | 3 | 100%
Programming of the Board | Sanjana | 80 | 1 | 100 | 1 | 100%
Testing of the program, Testing BLE mesh and Machine learning for character interpretation | Sanjana and Shekhar | 81 | 7 | 100 | 7 | 100%